Real world effort estimation...

---
No More Guessing
Effort Estimation with Jupyter Notebook
Sebastian Kübeck
Mastodon, LinkedIn, Twitter: @skuebeck
sebastian.kuebeck@aon.at
https://sebastiankuebeck.wordpress.com/

---
Terminology
An estimate is an approximation based on incomplete information.
An ambition is the commitment to do better than the estimate, if possible.
A target is a statement of a desirable business objective. E.g.
“We need to have Version 2.1 ready to demonstrate at a trade show in May.”
“We need to have this release stabilized in time for the holiday sales cycle.”
A commitment is a promise to deliver defined functionality at a specific level of quality by a certain date.
An offer is a conditional promise which becomes a binding contract if the offeree accepts it.
Liability

---
Parkinsons Law is an urban legend!
Originally, Parkinson's law is the adage that "work expands so as to fill the time available for its completion", and the title of a book which made it well-known.
However, in current understanding, Parkinson's law is a reference to the self-satisfying uncontrolled growth of the bureaucratic apparatus in an organization.
https://en.wikipedia.org/wiki/Parkinson's_law

---
Why not drop estimation at all?
2012: First use of #NoEstimates ....

---
Studies: Teams that don’t estimate are more productive!

---
#NoEstimates today
2023: #NoEstimates is dead!
Reasons:
Proponents could not agree on definitions and methodology.
Truism: It is not possible to think about the future in a reasonable way without any form of estimation.
It turned out that problems with estimates have the following reasons and they can not be solved by not estimating!
Lack of knowledge/education
Bad management practices

---
#NoEstimates Spin-Off
Estimations based on previous Data!
Estimation is done by the computer, based on previous project data.

---
Estimation based on Previous Data
Goal: Figure out tasks, estimating task size, summing up tasks, come up with a probability distribution instead of a number.
Probability (of completion)
0,1%
50%
90%
Time, Money

---
Estimation from previous Project Data
Questions
How to I get to an offer for a fixed priced project?
How much money can I make with this projects? What are the financial risks?
When will the project be finished?

---
Estimation from previous Project Data
Environment
Scrum is used as development process.
Development is orgenaized in Teams with 4-8 people.
Work is done within fixed time IntervaIs called Sprints.
Work is split in Stories as unit of Work.
Stories are estimated in Story Points, a relative metric that’s specific to a team.
Velocity is defined as Story Points completed per Sprint.
Environment
Scrum is used as development process.
Development is orgenaized in Teams with 4-8 people.
Work is done within fixed time IntervaIs called Sprints.
Work is split in Stories as unit of Work.
Stories are estimated in Story Points, a relative metric that’s specific to a team.
Velocity is defined as Story Points completed per Sprint.
https://www.scrum.org/resources/scrum-guide

---
Story Points
A
B
Flächeninhalt A:B ≈ 3:4
...in Story Points, this is 4:3, 8:6 or 40:30, every team usees their own story points

---
Problem: The velocity is not constant!
Velocity = Story Points/Sprint
???
now
Time
Sprint n+1
Sprint n+2 ...
Sprint n-2
Sprint n
...
Sprint n-1

---
Example: Fixed Proce Project
Given:
Projekt requires 50 Story Points
The velocity distribution is the same as in the past
To be determined:
Best Case: How many Sprints does it take to complete the project in an optimal situation? How likely ist this case?
Bad Case: How many sprints do I have to sell, not to make a loss with a probability of 95%?
Worst Case: What is the maximum number of Sprints required to complete the projcet? How likely ist this case?
Expected Gain: How many Sprints do I have to sell in order to make a profit?

---
Velocity
Assumption: Velocity distribution will not change in the future

---
Edge Cases from the Histogram
Best Case
Maximum Velocity: 25 Story Points
Number of Sprints for maximum Velocity: 50/25 = 2 Sprints
Probability:
(Frequency 25 Story Points/Number of Measurements)Sprints
   result: (2/11)2 = 3,31%
Worst Case:
Minimum Velocity: 1 Story Point
Number of Sprints at minumum Velocity: 50/1 = 50 Sprints
Probability:
(Probability 1 Story Points/Number of Measurements)Sprints
   result: (1/11)50 = 8,5x10-51
..way too improbable!

---
Determinsitc System
y
2
x
3
Calculation
z
5
Task: x, y known, calculate z.

---
Probabilistic System
Y
X
0,1%
50%
90%
0,1%
50%
90%
Calculation
Z
???
0,1%
50%
X,Y and Z are Random Variables!
Task: distribution of X, Y known, calculate distribution of Z.

---
Monte Carlo Approximation
yn
xn
0,1%
50%
90%
0,1%
50%
90%
Calculation
zn
0,1%
50%
1. Take n random samples xn, yn from Distributions X and y.
2. Calculate zn from xn, yn.
3. The histogram of zn will approximate Distribution of Z.

---
Monte Carlo Method
for Project outcomes
Random numbers with above distribution
= simulated Velocity = Story Points/Sprint
Sum up simulated Velocities until 50 Story Points are reached. Note the numner of Sprints

---
Burndown Graph
Burn Down Graph for 5 possible project outcomes...

---
Monte Carlo Methode
Generieren von Zufallszahlen mit gegebener Verteilung
Numpy (Python):
numpy.random.choice(a=Values, p=Propabilities)
 https://docs.scipy.org/doc/numpy-dev/reference/generated/numpy.random.choice.html
Excel:
Michael de la Maza: Monte Carlo Planning Improves Decision Making, InfoQ 2017:
https://www.infoq.com/articles/monte-carlo-planning

---
Number of Sprints required
Number of required Sprints for 1000 Project runs...

---
Histogramm of Simulated Projects
5000 simulated projects later....

---
Histogramm Evaluation
Average Case:
We make money starting at 50%, that means we have to sell at least
3 Sprints!
We could have calculated this immediately:
Average Velocity: 18.91
Average number of Sprintsl:
Story Points total/average Velocity
        result: 50/18.91 = 2.64, rounded up yields 3 Sprints!
Bad Case:
Probability > 95% corresponds to 1 – 0.05%
From the histogramm: 6 Sprints (Probability: 99.38%)
Expected gain: 6 – 2.64 = 3.36 Sprints

---
Conclusion
Best Case:
We need at least 2 Sprints to finish the project!
However, the propability is pretty low 3.31%!
Average Case:
We need to sell at least 3 Sprints to make money!
Bad Case:
We need at least 6 Sprints to be sure that we don’t loose money with a probability of 95%!
Worst Case:
Only if we sell 50 Sprints we can be 100% certain that we don’t loose money.
However, the probability that we actually need 50 Sprint is extremely unlikely.

---
Further Reading
Magically Predictable Software Production for Projects
Ralf Westphal, 2019
https://ralfw.de/magically-predictable-software-production-for-projects/
Monte Carlo Estimation for Kanban Projects
Software Estimation: Demystifying the Black Art
Steve McConnell, 2009
https://leventov.medium.com/excerpts-from-software-estimation-demystifying-the-black-art-9cf80e2b9977
Comprehensive introduction to Software Estimation
Forecasting and Simulating Software Development Projects
Troy Magennis 2011
https://github.com/FocusedObjective/FocusedObjective.Resources/blob/master/README.md

---
Planning without prior Data
How do I deal with the following situation?
New team or major change.
R&D Project.
No idea if it can be accomplished.
Not familiar with domain, technology

---
Planning without prior Data
Solution:
Don’t estimate Effort but Value!

---
Planning without prior Data
Process (yet unnamed)
Define goal
Figure out how much you are willing to invest to reach this goal.
Set up a budget based on defined investment.
Start working until...
goal is reached,
it is obvious that the goal cannot be reached,
The budget is used up.
Continue with 1

---
How to Estimate Value
Gilb Method
1. STAKEHOLDERS: Identify your most critical stakeholders.
2. OBJECTIVES: Identify the smart levels of their most critical value improvements.
3. STRATEGIES: Identify potential strategies for delivering planned value levels to
stakeholders, at lowest cost and risk.
4. SMALL STEPS: Decompose strategies into suitably smaller deliverable increments.
5. DELIVER VALUE: Attempt to deliver measurable value to some stakeholders.
6. LEARN: Measure results and costs; then decide if you are on track, or need to change something. Continue the process until all goals reached.
https://www.gilb.com/store/2W2zCX6z